## Sheet1
Critical Success Factors (CSF) | Source Requirement(s) | Technical Performance Measures (TPM) | Source Requirement | Required TPM Value | Current TPM Value
FIT/CSRR is able to manuever through a debris field. | FIT/CSRR - 15, 16, 17, 18, 39, 43, 48, 53, 58, 60 | Weight (Robot) | FIT/CSRR - 84 | ≤ 12 Pounds | N/A
FIT/CSRR is able to provide wireless camera feed, in the visual and infrared spectrum. | FIT/CSRR - 20, 21, 22 | Weight (System) | FIT/CSRR - 85 | ≤ 42 Pounds | N/A
FIT/CSRR is able to provide wireless two-way audio between the operator and the survivor. | FIT/CSRR - 24, 25, 26, 27.1, 27.2 | Deployment Time | FIT/CSRR - 34 | ≤ 5 Minutes | N/A
FIT/CSRR is able to operate at maximum duty cycle for one hour. | FIT/CSRR - 32 | Speed | FIT/CSRR - 15 | ≥ 1 ft/s | N/A
FIT/CSRR is able to transmit and recieve data wirelessly. | FIT/CSRR - 62, 64, 65 | Size | FIT/CSRR - 82 | ≤ 12in x 12in x 12in | N/A
FIT/CSRR is IP-65 compliant. | FIT/CSRR - 91 | Power Required (Mission Duration) | FIT/CSRR - 32 | ≥ 1 hour operating time | N/A
FIT/CSRR end cost is less than or equal to $10,000. | N/A | Wireless Connection Range | FIT/CSRR - 39 | ≥ 50 Meters (164 Feet) | N/A
FIT/CSRR preliminary design completed by the end of fall semester, and the prototype completed by the end of spring semester. | N/A | Camera Feeds | FIT/CSRR - 20/21 | 30 - 60 Frames per Second | N/A
FIT/CSRR has well defined adjacent systems and system interfaces. | N/A | Charge Time | FIT/CSRR - 35 | ≤ 1 Hour | N/A